## LGTAWEBDEV Release Plan
Magazine Deployment Plan
DEV Team: Tan Nguyen, Anh Tran, Do Ho, Chien Luong
IT Team: Vu Nguyen
Test Team: Hien Huynh, Ngan Truong, Thinh Nguyen
# | Task | Description | Owner | Plan Executed Date | Status | Notes
A | Prepare for deploy new Magazine
1 | Export source code and Database | - Export source code and database from Live server to build Magazine Beta | IT Team | 2017-10-19 | Done
2 | Build Magazine Beta for test | - Get database and source code form Live to create Magazine Beta on Local - Update Categories and title for each post. - Update Thumbnail for each post. - Upgrade Wordpress and Plug-in. - Edit theme's layout . - Redirect the old URL to new URL - ... | DEV Team | 2017-10-23
3 | Test | - Test Categories and Title of Post - Test Thumbnail of Post - Test GTM code - Test all Features(Subscribe Form, Ads popup, Popular post, Related post, popular topic, archives page,…) - Test Theme's Layout - Test URL Redirection - ... | Test Team | 2017-10-26
4 | Export newest Database Live | -Export newest Database Live to merge Comment | IT Team | 2017-10-31
5 | Merge Comment |  | DEV Team | 2017-10-31
6 | Prepare source code and database for deploy | - Config database for Live site ( Site URL, Site Link,.. ) - Config database connect tion | DEV Team | 2017-10-31
B | Deploy Magazine to Production Server
1 | Backup Source Code from Production server | * Backup Magazine source code and database | IT Team | 2017-11-01
2 | Deploy new version of Magazine Beta site to Production server | 1. Export database of Magazine Beta site and import to database Live server. 2. Removing old Magazine source code. 3. Copy and paste source code of Magazine Beta into deploying folder of Magazine Live Server 4. Try to access to http://www.logigear.com/magazine/ to verify new site | DEV Team/IT Team | 2017-11-01
3 | Check the deployment | - Browse some Magazine pages to verify they work well - check all functions | Test Team | 2017-11-01